## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis |  |  | Overhead
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
TL-1 Palak | 11200 |  | 11200 | 7000 |  | 7000 | 2500 | 1200 | 1300 | 200 | 200 | 0 | 1200 | 700 | 500
TL-2 Spencer | 11200 |  | 11200 | 7000 |  | 7000 | 2500 | 1500 | 1000 | 100 | 600 | -500 | 1200 | 2500 | -1300
TL-3 Cole | 11200 |  | 11200 | 7000 |  | 7000 | 2500 | 1500 | 1000 | 200 | 400 | -200 | 1200 | 0 | 1200
TL-4 Shaun | 11200 |  | 11200 | 7000 |  | 7000 | 2500 | 1500 | 1000 | 200 | 600 | -400 | 1200 | 1000 | 200
TL-5 Hongxi | 11200 |  | 11200 | 7000 |  | 7000 | 2500 | 1500 | 1000 | 200 | 200 | 0 | 1200 | 0 | 1200
TL-6 Shreeya | 11200 |  | 11200 | 7000 |  | 7000 | 2500 | 1400 | 1100 | 200 | 200 | 0 | 1200 | 0 | 1200
Total | 67200 | 0 | 67200 | 42000 | 0 | 42000 | 15000 | 8600 | 6400 | 1100 | 2200 | -1100 | 7200 | 4200 | 3000

## Gantt
| predicted time(hrs) | time spent(hrs) | Status | complete | complete | this week | planned
TL-Palak |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59
Unity Instalation/Pong Game | 4 | 4 | complete | complete 1: complete; complete 2: complete; this week 3: complete; planned 4: complete
Sound Design | 8 |  | planned | planned 5: planned; planned 6: planned; planned 7: planned; planned 8: planned; planned 9: planned; planned 10: planned; planned 11: planned; planned 12: planned
Sound Implementation | 5 |  | planned | planned 13: planned; planned 14: planned; planned 15: planned; planned 16: planned; planned 17: planned
Over World Enemy readouts | 10 |  | planned | planned 18: planned; planned 19: planned; planned 20: planned; planned 21: planned; planned 22: planned; planned 23: planned; planned 24: planned; planned 25: planned; planned 26: planned; planned 27: planned
totals | 27 | 4
TL-2 Spencer
Unity Instalation/Pong Game | N/A | N/A | complete
Template Overworld Map Creation | 1 | 1 | complete | complete 1: complete
Player Movement | 2 | 4 | complete | complete 2: complete; this week 3: complete; planned 4: complete; planned 5: complete
Battle Physics - Targeting | 7 | 6 | complete | planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete; planned 10: complete; planned 11: complete; planned 12: planned
Battle Physics - Taking Damage | 4 |  | planned | planned 13: planned; planned 14: planned; planned 15: planned; planned 16: planned
Player Unit Firing | 6 |  | planned | planned 17: planned; planned 18: planned; planned 19: planned; planned 20: planned; planned 21: planned; planned 22: planned
totals | 20 | 11
TL-3 Cole
Unity Instalation/Pong Game | 2 | 2 | complete | complete 1: complete; complete 2: complete
scene change | 4 | 3 | complete | this week 3: complete; planned 4: complete; planned 5: complete
player ship | 6 |  | planned | planned 6: planned; planned 7: planned; planned 8: planned; planned 9: planned; planned 10: planned; planned 11: planned
sprites | 3 |  | planned | planned 12: planned; planned 13: planned; planned 14: planned
Upgrades System | 8 |  | planned | planned 15: planned; planned 16: planned; planned 17: planned; planned 18: planned; planned 19: planned; planned 20: planned
totals | 23 | 5
TL-4 Shaun
Unity Instalation/Pong Game | 3 | 3 | complete | complete 1: complete; complete 2: complete
Health | 3 | 6 | complete | this week 3: complete; planned 4: complete; planned 5: complete; planned 6: complete; planned 7: complete; planned 8: complete
Main Menu | 2 |  | planned | planned 9: planned; planned 10: planned
Pause | 4 |  | planned | planned 11: planned; planned 12: planned; planned 13: planned; planned 14: planned
Pause on Death | 7 |  | planned | planned 15: planned; planned 16: planned; planned 17: planned; planned 18: planned; planned 19: planned; planned 20: planned; planned 21: planned
totals | 19 | 9
TL-5 Hongxi
Unity Instalation/Pong Game | 3 | 3 | complete | complete 1: complete; complete 2: complete; this week 3: complete
Overworld Enemies | 8 | 1 | complete | planned 4: complete
AI Enemy Targeting/Attacking | 4 | 1 | complete | planned 5: complete
AI Enemy Ship Variants | 4 |  | planned | planned 6: planned; planned 7: planned; planned 8: planned; planned 9: planned
Restart On Player Death/Sink | 2 |  | planned | planned 10: planned; planned 11: planned
totals | 21 | 4
TL-6 Shreeya
Unity Instalation/Pong Game | N/A | N/A | complete
Over World Map Collision | 3 | 3 | complete | complete 1: complete; complete 2: complete; this week 3: complete
Battle/Map Maps | 8 |  | planned | planned 4: planned; planned 5: planned; planned 6: planned; planned 7: planned; planned 8: planned; planned 9: planned; planned 10: planned; planned 11: planned
| 11 | 3
group totals (hrs) | 89 | 29
group totals ($) | 8900 | 2900

## Meetings
| Date | Aug. 30 | Sept. 2 | Sept. 13 | Sept. 15 | Sept. 21 | Sept. 22 | Sept. 23 | Sept. 29 | 2023-10-04 | Oct. 20
| Purpose | First Meeting | Ananlysis Planning | Ananlysis Integration | Ananlysis presentation practice | Initial Set-up | Initial Set-up | Initial Set-up | Initial Release | Team Lead 2 demo practice | Test Code Integrateion
| Hours | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 8
TL-1 Palak | 12 | ü | ü | ü | ü | ü | ü | ü
TL-2 Spencer | 15 | ü | ü | ü | ü | ü | ü | ü | ü | ü
TL-3 Cole | 15 | ü | ü | ü | ü | ü | ü | ü | ü | ü
TL-4 Shaun | 15 | ü | ü | ü | ü | ü | ü | ü | ü | ü
TL-5 Hongxi | 15 | ü | ü | ü | ü | ü | ü | ü | ü | ü
TL-6 Shreeya | 14 | ü | ü | ü | ü | ü | ü | ü | ü
Total | 86 | 6 | 6 | 12 | 12 | 12 | 12 | 12 | 10 | 4 | 0
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
TL-1 Palak | Individual schedule | 2 | 2 | bar: 2
| Subtotal | 2 | 2
TL-2 Spencer | Individual schedule | 1 | 6 | bar: 1 to 2
| Subtotal | 1 | 6
TL-3 Cole | Individual schedule | 2 | 4 | bar: 1
| Subtotal | 2 | 4
TL-4 Shaun | Individual schedule | 2 | 6 | bar: 1 to 2
| Subtotal | 2 | 6
TL-5 Hongxi | Individual schedule | 2 | 2 | bar: 1 to 2
| Subtotal | 2 | 2
TL-6 Shreeya | Individual schedule | 2 | 2 | bar: 1 to 2
| Subtotal | 2 | 2
| Total | 7 | 14
red is dependent on others

## Overhead
| TL-1 Palak | TL-2 Spencer | TL-3 Cole | TL-4 Shaun | TL-5 Hongxi | TL-6 Shreeya
Training | 4 |  |  | 3
SA Preesentation Prep | 2 | 10 |  | 7
Software Specialist Presnetaion Prep | 1 | 15
Team Lead Presentation Prep
Oral Exam Prep
Post Mortum Presentation Prep
Total | 7 | 25 | 0 | 10 | 0 | 0