## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis |  |  | Overhead
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
TL-1 Palak |  |  | 0 |  |  | 0 |  | 600 | -600 | 200 | 200 | 0 |  | 0 | 0
TL-2 Spencer |  |  | 0 |  |  | 0 |  | 600 | -600 | 100 | 150 | -50 |  | 0 | 0
TL-3 Cole |  |  | 0 |  |  | 0 |  | 600 | -600 | 200 | 300 | -100 |  | 0 | 0
TL-4 Shaun |  |  | 0 |  |  | 0 |  | 600 | -600 | 200 | 150 | 50 |  | 0 | 0
TL-5 Hongxi |  |  | 0 |  |  | 0 |  | 600 | -600 | 200 | 200 | 0 |  | 0 | 0
TL-6 Shreeya |  |  | 0 |  |  | 0 |  | 600 | -600 | 200 | 200 | 0 |  | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | -3600 | 1100 | 1200 | -100 | 0 | 0 | 0

## Gantt
| predicted time(hrs) | time spent(hrs) | Status | key | complete | this week | planned
TL-Palak |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59
Unity Instalation/Pong Game | N/A | N/A | complete
Sound Design | 4 |  | planned | key 1: planned; complete 2: planned; this week 3: planned; planned 4: planned
Sound Implementation | 2 |  | planned | planned 5: planned; planned 6: planned
Over World Enemy readouts | 5 |  | planned | planned 7: planned; planned 8: planned; planned 9: planned; planned 10: planned; planned 11: planned
totals | 11 | 0
TL-2 Spencer
Unity Instalation/Pong Game | N/A | N/A | complete
Battle Physics | 8 |  | planned | key 1: planned; complete 2: planned; this week 3: planned; planned 4: planned; planned 5: planned; planned 6: planned; planned 7: planned; planned 8: planned
AI Enemy Ship | 5 |  | planned | planned 9: planned; planned 10: planned; planned 11: planned; planned 12: planned; planned 13: planned
AI Enemy Upgrades | 4 |  | planned | planned 14: planned; planned 15: planned; planned 16: planned; planned 17: planned
totals | 17 | 0
TL-3 Cole
Unity Instalation/Pong Game | 2 | 2 | complete | key 1: complete; complete 2: complete
player ship | 6 |  | planned | this week 3: planned; planned 4: planned; planned 5: planned; planned 6: planned; planned 7: planned; planned 8: planned; planned 9: planned
sprites | 3 |  | planned | planned 10: planned; planned 11: planned; planned 12: planned
Upgrades System | 8 |  | planned | planned 13: planned; planned 14: planned; planned 15: planned; planned 16: planned; planned 17: planned; planned 18: planned; planned 19: planned; planned 20: planned
totals | 19 | 2
TL-4 Shaun
Unity Instalation/Pong Game | 3 | 3 | complete | key 1: complete; complete 2: complete
Main Menu | 2 |  | planned | this week 3: planned; planned 4: planned
Pause | 4 |  | planned | planned 5: planned; planned 6: planned; planned 7: planned; planned 8: planned
Health | 3 |  | planned | planned 9: planned; planned 10: planned; planned 11: planned
Pause on Death | 7 |  | planned | planned 12: planned; planned 13: planned; planned 14: planned; planned 15: planned; planned 16: planned; planned 17: planned; planned 18: planned
totals | 19 | 3
TL-5 Hongxi
Unity Instalation/Pong Game | 3 | 3 | complete | key 1: complete; complete 2: complete; this week 3: complete
Overworld Enemies | 8 |  | planned | planned 4: planned; planned 5: planned; planned 6: planned; planned 7: planned; planned 8: planned; planned 9: planned; planned 10: planned; planned 11: planned
AI Enemy Ship Variants | 4 |  | planned | planned 12: planned; planned 13: planned; planned 14: planned; planned 15: planned
Restart On Player Death/Sink | 2 |  | planned | planned 16: planned; planned 17: planned
totals | 17 | 3
TL-6 Shreeya
Unity Instalation/Pong Game | N/A | N/A | complete
Over World Map | 3 |  | planned | key 1: planned; complete 2: planned; this week 3: planned
Battle/Map Maps | 6 |  | planned | planned 4: planned; planned 5: planned; planned 6: planned; planned 7: planned; planned 8: planned; planned 9: planned
| 9 | 0 |  | planned 10: planned; planned 11: planned; planned 12: planned; planned 13: planned; planned 14: planned; planned 15: planned; planned 16: planned; planned 17: planned; planned 18: planned
group totals (hrs) | 66 | 5
group totals ($) | 6600 | 500

## Meetings
| Date | Aug. 30 | Sept. 2 | Sept. 13 | Sept. 15 | Sept. 21 | Sept. 22 | Sept. 23 | Sept. 29 | Oct. 4 | Oct. 20
| Purpose | First Meeting | Ananlysis Planning | Ananlysis Integration | Ananlysis presentation practice | Initial Set-up | Initial Set-up | Initial Set-up | Initial Release | Team Lead 2 demo practice | Test Code Integrateion
| Hours | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 6 | 1 | 8
TL-1 Palak | 6 | ü | ü | ü | ü
TL-2 Spencer | 6 | ü | ü | ü | ü
TL-3 Cole | 6 | ü | ü | ü | ü
TL-4 Shaun | 6 | ü | ü | ü | ü
TL-5 Hongxi | 6 | ü | ü | ü | ü
TL-6 Shreeya | 6 | ü | ü | ü | ü
Total | 36 | 6 | 6 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
TL-1 Palak | Individual schedule | 2 | 2 | bar: 2
| Subtotal | 2 | 2
TL-2 Spencer | Individual schedule | 1 | 1.5 | bar: 1 to 2
| Subtotal | 1 | 1.5
TL-3 Cole | Individual schedule | 2 | 3 | bar: 1
| Subtotal | 2 | 3
TL-4 Shaun | Individual schedule | 2 | 1.5 | bar: 1 to 2
| Subtotal | 2 | 1.5
TL-5 Hongxi | Individual schedule | 2 | 2 | bar: 1 to 2
| Subtotal | 2 | 2
TL-6 Shreeya | Individual schedule | 2 | 2 | bar: 1 to 2
| Subtotal | 2 | 2
| Total | 7 | 8.5
red is dependent on others

## Overhead
| TL-1 Palak | TL-2 Spencer | TL-3 Cole | TL-4 Shaun | TL-5 Hongxi | TL-6 Shreeya
Training
SA Preesentation Prep
Software Specialist Presnetaion Prep
Team Lead Presentation Prep
Oral Exam Prep
Post Mortum Presentation Prep
Total | 0 | 0 | 0 | 0 | 0 | 0